## NimbusPay Risk Register
Risk ID | Date Raised | Asset | Category | Risk Description | Likelihood (1-5)/ Impact (1-16) | Suggested Controls | Practical Implementation | Framework | Owner | Status (Open/In Progress/Closed) | Next Review
1 | 2026-02-02 | AWS | Tech/cybersecurity | Human error in configuring/using Amazon S3 could lead to exposing data to the public. This could lead to easy access for attackers to steal the data which would result in damage to stored information assets such as customer data, analytics, etc. resulting financial and reputational damage. | 5 and 16 | CM-8(1), MP-2, MP-6(1), AC-3(7), AT-2(2) | Maintain an automated inventory of all S3 assets and data classifications. Restrict access to S3 buckets by enforcing role-based access control. Restrict physical and logical access to media containing sensitive data. Implement a formal sanitization process before any media is reused or disposed of. Implement security awareness training that includes the consequences of S3 misconfiguration and improper asset handling. | NIST SP 800-53 Rev. 5 | Bill - Tech Admin | Open | Quarterly
2 | 2026-02-04 | AWS | Tech/cybersecurity | Ransomware attackers gaining admin access to AWS system as a result of limited visibility in logging + insufficient incident response process can encrypt or manipulate customer PII, payment details, etc. This will lead to signigicant financial cost to recover the information. There will be operational disruption and loss of customer trust when customers find out that the organization was victim to a cyberattack. | 4 and 16 | SI-3(1), SI-4(2), IR-4(1), AU-12(1), AC-2(4) | Deploy and configure anti-malware tools with automatic definition updates to detect ransomware. Implement SIEM with automated real-time alerting on suspicious activity and enable AWS CloudTrail for full logging coverage. Configure automated audit logging of all admin account creation, modification, enabling, disabling, and removal actions. Properly implement the incident response process including tabletop exercises to prepare the team to contain and recover from ransomware events. | NIST SP 800-53 Rev. 5 | Jennifer - incident response lead | Open | Quarterly
3 | 2026-02-06 | AWS | Tech/cybersecurity | Hackers gaining access to CI/CD pipeline as a result of weak access controls or lack of code integrity validation could result in unauthorized changes to the code in our application. Hackers can restrict features, deploy malicious updates, etc leading to damage to the software which will lead to financial costs to rebuild and reputational damage when customers are frustrated with our application. | 3 and 8 | AC-2(7), AC-3(7), AC-6(1), SI-7(1), CM-3(1) | Review all accounts with access to the CI/CD pipeline and enforce role-based access control so that only authorized developer and admin roles can push or merge changes. Implement automated code integrity validation to detect unauthorized changes to application code. Enforce an automated configuration change review process so that all pipeline configuration changes are logged, reviewed, and approved before taking effect. | NIST SP 800-53 Rev. 5 | Ritchie - information security lead analyst | Open | Quarterly
4 | 2026-02-08 | AWS | Tech/software development | Developers tend to push hotfixes directly into production which could lead to rushed deployment across the application. There could be bugs or issues that would be pushed onto the platform without being checked. This could lead to frustration of end users and reputational damage. | 3 and 8 | SA-15(1), CM-3(2), SA-11(1), SA-8(3), SI-2(2) | Create a mandatory change management procedure that all developers must follow before pushing any hotfix to production. Critical changes must be reviewed for adverse effects on operations and security before release. Integrate security testing at every stage of the development lifecycle. Apply secure engineering principles as a standard part of the development process if needed. Implement automated tracking of software flaws discovered post-deployment and enforce timely remediation. | NIST SP 800-53 Rev. 5 | Leyla - software development manager | Open | Quarterly
5 | 2026-02-10 | People/Process | Process/Risk Management | Lack of formal vendor risk management program could lead to onboarding vendors who have not been certified as compliant or who have not gained proper certificates. Working with an unreliable vendor would lead to liability if an incident were to occur, legal penalties, and reputational damage. | 3 and 8 | SR-3(1), SR-5(1), SA-9(1), SA-4(1), SR-6(1) | Document and implement a formal vendor risk management program. Embed defined information security requirements into all vendor contracts and procurement agreements. Require vendors to comply with NimbusPay's security requirements on an ongoing basis and monitor compliance after onboarding. Conduct formal periodic audits or assessments of vendors to verify their credentials, certifications, and security posture remain valid. | NIST SP 800-53 Rev. 5 | Shawn - risk management lead | Open | Quarterly
6 | 2026-02-10 | People/Process | IAM/cybersecurity | Inconsistent access reviews could lead to an internal incident because a maliciously intended employee used their unrevoked priviledges to take unauthorized actions. This could lead to malfunctions/failures in systems, stealing of data, etc causing operational disruption, as well as financial damage depending on the type of disruption caused. | 3 and 8 | AC-2(3), AC-6(7), IA-4(4), AC-5, IA-5(1) | Update the access review process and implement it consistently across all departments. Configure automated disabling of accounts that have been inactive beyond a defined threshold. Conduct dedicated periodic reviews of privileged user accounts specifically, confirming that elevated access remains necessary and appropriate. Enforce separation of duties. Implement automated management of user identifiers including timely deactivation when employees change roles or leave the organization. Enforce password and credential policies across all accounts. | NIST SP 800-53 Rev. 5 | Jake - Info Systems Admin | Open | Quarterly
7 | 2026-02-10 | People/Process | Process/cybersecurity | Lack of incident response testing causes a lack of preparation of employees. Other maturity issues such as a lack of proper root cause analysis or control implementation, leads to repeated incidents and vulnerability in incident response systems. This would lead to financial damage to repair compromised systems or recover compromised data. It could also cause customer churn and distrust when customers learn of repeated incidents. | 5 and 16 | IR-2(1), IR-4(1), IR-5(1), IR-6(1), IR-8(1) | Implement regular incident response training. Refine the incident response process to include structured handling procedures with proper root cause analysis performed. Define and document clear reporting procedures so that all incidents are reported consistently using a standardized format. Formalize the incident response plan with clearly defined roles, responsibilities, and escalation paths, and review the plan at least annually. | NIST SP 800-53 Rev. 5 | Jennifer - incident response lead | Open | Quarterly
8 | 2026-02-15 | AWS | Backup/disaster recovery | Backups are not regularly tested. This leads to lack of preparation for data loss incidents. There will then be financial costs to recover data when incidents occur. It could lead to legal penalties for not protecting data, as well as reputational impact to the company. | 4 and 16 | CP-9(1), CP-10(2), CP-4(1), CP-2(1) | Implement a scheduled backup process for all critical systems and data in accordance with policy. Test backups regularly through documented restoration exercises to confirm that recovery is actually possible within acceptable timeframes. Document the backup and recovery procedures within a formal contingency plan that is coordinated with the incident response and disaster recovery plans. | NIST SP 800-53 Rev. 5 | Nitika - Disaster Recovery specialist | Open | Quarterly
9 | 2026-02-15 | People/Process | Training/cybersecurity | Security awareness training is informal leading to a lack of consistent preparation across employees. This leaves the enterprise vulnerable to phishing attacks and other social engineering attacks. | 3 and 8 | AT-2(2), AT-3(1), AT-4, PL-4(1) | Implement a monthly organization-wide class or webinar that includes specific coverage of phishing, social engineering, and insider threat awareness. Supplement general training with role-based security training for employees with elevated system access or security responsibilities. Maintain training completion records for all employees and track who has and has not completed required training. Require all employees to read and formally acknowledge the rules of behavior and acceptable use policy as part of the onboarding and annual training process. | NIST SP 800-53 Rev. 5 | Ahmed - employee training manager | Open | Quarterly
10 | 2026-02-15 | People/Process | Logging/cybersecurity | Logging and monitoring visibility is limited leading to a false sense of safety and blindness to potential cyber attacks. This could lead to financial costs if incidents were to occur and reputational costs if not resolved. | 5 and 16 | AU-2(1), AU-3(1), AU-6(1), AU-12(1), SI-4(2) | Configure all systems to generate audit records that contain the required content for every logged event. Deploy SIEM and enable AWS CloudTrail, configuring automated real-time analysis and alerting for suspicious activity. Implement a weekly human review of logs to catch anomalies that automated tools may miss. | NIST SP 800-53 Rev. 5 | Zara - system admin | Open | Quarterly
11 | 2026-02-15 | People/Process | IAM/cybersecurity | Hackers gaining access to GitHub repositories by stealing usernames and passwords either by social engineering or by lack of encryption, can cause changes in historical data. This leads to the spread of wrong information among engineers leading to confusion and chaos. The resulting lack of productivity and operational disruption can impact business functions leading to financial/reputational impact if functions slow down or issues are not resolved quickly leading to customer frustration and distrust. | 5 and 8 | SI-3(1), SC-8(1), SC-13(1), SC-28(1), CP-9(1), AT-2(2) | Deploy anti-malware and endpoint protection tools on all systems with access to GitHub repositories, ensuring definitions are automatically updated. Encrypt all data in transit using approved cryptographic mechanisms to protect credentials from interception. Ensure firewalls and IDS are configured and up to date to detect unauthorized access attempts to repositories. Implement regular automated backups of all critical repository data. Deliver security awareness training that specifically covers social engineering tactics used to steal credentials. | NIST SP 800-53 Rev. 5 | Jennifer - incident response lead | Open | Quarterly
12 | 2026-02-17 | Data | Encryption/cryptography | One risk item that builds off of NimbusPay's assets is encryption. Encryption must be checked because data must be encrypted both in motion and at rest. Assets such as employee credentials, privileged admin account credentials and API keys must be protected as a cyber attack stealing these and acting on behalf of an employee will have financial and reputational consequences. | 3 and 8 | SC-28(1), SC-8(1), SC-13(1), SC-12(1) | Review encryption implementations to confirm that employee credentials, privileged admin credentials, and API keys are protected using FIPS-validated cryptographic algorithms. Establish and enforce a formal cryptographic key management process covering the full key lifecycle so that compromised or expired keys cannot be exploited. | NIST SP 800-53 Rev. 5 | Jongin - cryptography manager | Open | Quarterly
13 | 2026-02-17 | Third Parties | Third Party Dependecies | All third parties must have proof of being compliant with legal requirements. They also must have proper GRC and cybersecurity functions. Operating with third parties without these pose a risk that the enterprise will be liable if these third parties have a breach. | 3 and 8 | SR-3(1), SA-9(1), SR-5(1), SR-6(1), SA-4(10) | Implement a formal review and audit process for all third parties to verify that they hold current compliance certifications, operate a formal risk management program, and maintain a dedicated cybersecurity function. Vet and select vendors using a defined set of security criteria before onboarding begins. Require in contracts that all third parties use only approved cryptographic standards when handling NimbusPay data. Monitor third-party compliance on an ongoing basis after onboarding. | NIST SP 800-53 Rev. 5 | Chan - Third Party Risk Lead | Open | Quarterly
14 | 2026-02-17 | Third Parties | Third Party Dependencies | There must be clear policies outlining how applications and tools like Slack and Jira can be used. If passwords/sensitive information is shared through these, there is risk of a cyber attack or an internal incident causing the company to be fined, liable, and there will be operational disruption. | 3 and 8 | SC-7(5), SC-8(1), SC-13(1), AC-17(1), PL-4(1) | Create or update policies governing the safe and acceptable use of messaging and project management tools such as Slack and Jira. Configure boundary protection using a deny-by-default posture so that only approved traffic and tools can communicate across NimbusPay's network. Enforce encryption in transit for all data sent through these tools, particularly when connected to public networks. Implement monitoring and controls for all remote access connections to ensure they meet security requirements. | NIST SP 800-53 Rev. 5 | Benjamin - Senior GRC Analyst | Open | Quarterly
15 | 2026-02-17 | Third Parties | Third Party Dependencies | Customer onboarding should be monitored closely and ensuring compliance and other documentation is legit is paramount as to not fall into legal liability, penalties and reputational damage. | 3 and 4 | SR-3(1), SA-9(1), SA-4(1), SR-6(1), CA-7(1) | Document all relevant information security requirements that customers being onboarded must meet, and include these requirements formally in onboarding agreements. Assess each customer's risk posture before onboarding. Verify that customers have legitimate compliance documentation, a functioning risk management program, and adequate cybersecurity controls before onboarding is completed. Monitor customer compliance on an ongoing basis after onboarding. | NIST SP 800-53 Rev. 5 | Ali - Third Party Compliance Manager | Open | Quarterly
16 | 2026-02-17 | Third Parties | Third Party Dependencies | Slow onboarding process can cause customer churn/drop off because of frustration about tedius processes. This will cause a loss of business and revenue. | 3 and 4 | Review/audit onboarding processes to decide ways to make it more efficient without compromising effectiveness | Brainstorm ideas to create a quick and seamless onboarding process for customers. | Custom Control | Drake - Customer onboarding specialist | Open | Quarterly
17 | 2026-02-18 | people/process | onboarding/operational risk | If NimbusPay fails to be compliant with legal and regulatory requirements for onboarding, this can lead to fines, penalties, and reduced revenue. If customers find that NimbusPay is not compliant, this can create reputational distrust. | 3 and 8 | PL-1(1), CA-2(1), SA-4(1), PM-9, RA-3(1) | Review and update NimbusPay's onboarding policies to explicitly address all applicable legal and regulatory compliance requirements, ensuring policies are current and enforced consistently. Embed defined compliance requirements into all customer onboarding agreements. Perform formal risk assessments that treat regulatory onboarding requirements as risk scenarios so that gaps are identified and addressed proactively before they become violations. | NIST SP 800-53 Rev. 5 | Anne - Compliance analst lead | Open | Quarterly
18 | 2026-02-18 | People/Process | finances/operational risk | If NimbusPay fails to record financial gains/losses correctly, it can lead to inaccurate numbers which impacts business decisions regarding financial goals and it will also lead to legal issues. | 4 and 8 | Ensure financial reporting is accurate by automating process, standardizing procedures, and implementing segregation of duties. | Automate and standardize processes for financial reporting and ensure there is a human in the loop for periodic review. | custom Control | Mary - Lead Financial Analyst | Open | Quarterly
19 | 2026-02-19 | People/Process | Process/cyberscurity | Poor threat identification by SOC teams (this should be checked because incident response process is only documented and not being acted upon properly) through a system not being configured effectively can lead to a false sense of safety and more attacks. This can lead to financial damage, operational disruption, and loss of integrity. | 3 and 8 | RA-3(1), SI-4(2), IR-4(1), CA-7(1), RA-5(2) | Conduct formal risk assessments that include threat identification and modeling to ensure the SOC has a documented and current picture of the threat landscape. Implement recurring vulnerability scans at a defined frequency. Deploy and properly configure SIEM, logging, and IDS systems with automated real-time analysis. Move the incident response process from documentation into active practice — ensure the SOC is executing the process. Establish a continuous monitoring program that keeps security controls, threat data, and system configurations under active review on an ongoing basis. | NIST SP 800-53 Rev. 5 | Dhruv - SOC Lead | Open | Quarterly
20 | 2026-02-19 | People/Process | Process/operational risk | Inaccurate reporting of cybersecurity/disaster recovery incidents will lead to false sense of safety and result in repeated incidents which catch the team offguard. This leads to more damage to assets and will have financial repercussions. | 4 and 8 | CP-2(1), CP-10(2), IR-8(1), AU-6(1), CP-4(1) | Standardize all cybersecurity and disaster recovery incident reporting using consistent formats, templates, and procedures so that reports are accurate and comparable. Review incident reports periodically to extract lessons learned and implement corrective measures to prevent repeated incidents. Document a formal contingency plan that coordinates DR and IR reporting procedures and is reviewed and updated at a defined interval based on policy. Conduct periodic DR plan tests to validate that recovery procedures work as documented and that transaction-level recovery of financial and customer data is achievable. | NIST SP 800-53 Rev. 5 | Mariam- Cybersecurity lead | Open | Quarterly
21 | 2026-02-25 | AWS | cybersecurity | An employee misconfigures access controls or network exposure of RDS databases. This will enable unauthorized access to financial/customer data leading to cyberattacks after data is stolen. | 2 and 8 | AC-3(7), SC-7(5), SI-3(1), AC-6(1), MP-2 | Review and update access configurations for all AWS RDS databases, enforcing role-based access controls. Apply least privilege to all database accounts and remove any excessive permissions. Segment the network and configure boundary protection using a deny-by-default posture to prevent unauthorized network exposure of RDS instances. Deploy and maintain anti-malware tools with automatic updates on all systems that interact with the database layer. Restrict physical and logical access to media and storage containing sensitive data. | NIST SP 800-53 Rev. 5 | Leyla - software development manager | Open | Quarterly
22 | 2026-02-25 | Web application | Software development | NimbusPay’s web app front end is created with React. The risks associated with this include cross site scripting and other injection attacks because of a lack of proper input validation. An employee failing to configure and sanitize adequately can allow for sensitive information to be stolen and malicious actions to be made against the NimbusPay app. | 2 and 8 | CM-8(1), SI-3(1), SA-11(1), AC-3(7), AT-2(2) | Maintain an automated inventory of all web application components and assets, including React dependencies, so that misconfigured or outdated components are identified promptly. Enforce role-based access control on who is permitted to modify application configuration and deploy changes to the frontend. Implement thorough security testing of all input fields as part of the developer testing process, and perform sanitization checks periodically. Deploy and maintain anti-malware tools to detect malicious code that may be introduced through the frontend. | NIST SP 800-53 Rev. 5 | Dan - Software development lead | Open | Quarterly
23 | 2026-02-25 | Web application | Software development | Developers use Node.js to execute java script insecurely causing vulnerability because of poor authentication and weak rate limiting. This could allow for code injection attacks or brute force attempts. All third-party integrations must have controls in place to combat vulnerabilities and mitigate risks with the third-party tools/integrations/vendors. | 3 and 8 | SA-9(1), SA-11(1), CM-3(1), SI-2(2), CA-7(1) | Create or enforce a configuration policy for Node.js that mandates secure authentication patterns, rate limiting, and input validation across all endpoints. Require that all third-party integrations meet defined security requirements and are assessed before being connected to NimbusPay's application. Implement developer security testing throughout the Node.js build process to catch authentication weaknesses and injection vulnerabilities before they reach production. Track all identified software flaws with automated tooling and enforce timely remediation so vulnerabilities do not accumulate. Establish continuous monitoring of Node.js application behavior and third-party integration activity to detect anomalies. | NIST SP 800-53 Rev. 5 | Leyla - software development manager | Open | Quarterly
24 | 2026-02-26 | Web application | Software development | Developers’ use of third-party libraries in Node.js application could introduce new vulnerabilities if this use is not regulated. Malicious packages can be downloaded and can cause damage if they aren’t from reliable organizations. | 2 and 8 | SR-3(1), SR-5(1), SA-9(1), CM-3(1), SI-2(2) | Create or enforce a policy that governs the use of third-party libraries in NimbusPay's Node.js application, specifying that only packages from vendors approved by the security team may be downloaded and used. Require that all third-party libraries meet NimbusPay's defined security requirements on an ongoing basis. Enforce a formal review and approval process before any new library or dependency is added to the application, preventing shadow IT practices. Implement automated vulnerability scanning of all third-party dependencies to track known vulnerabilities in packages currently in use and enforce timely remediation or replacement when a vulnerability is discovered. | NIST SP 800-53 Rev. 5 | Dan - Software development lead | Open | Quarterly
25 | 2026-02-27 | Web application | Software development | Developers improperly authenticate APIs which may allow attackers to access and manipulate financial transactions leading to fraud, data exposure, financial loss, and reputational damage to NimbusPay. | 3 and 8 | SA-11(1), SA-8(3), AC-3(7), SI-3(1), AT-2(2) | Enforce role-based access control on all APIs so that only authenticated and authorized roles can initiate or approve financial transactions. Apply secure engineering principles as a standard design requirement for all API development at NimbusPay. Deploy anti-malware tools to detect malicious activity targeting the API layer. | NIST SP 800-53 Rev. 5 | Dan - Software development lead | Open | Quarterly
26 | 2026-02-27 | Legal Compliance | Legal/Regulatory Requirements | NimbusPay fails to be compliant with local laws in different states which may cause legal/regulatory penalties. This can slow business in other states or prevent them from doing business in other states. | 3 and 4 | PL-1(1), PM-9, CA-2(1), RA-3(1), SA-9(1) | Update NimbusPay's policies to address state-specific legal and regulatory requirements across all US states where NimbusPay does business. Develop and maintain an organization-level risk management strategy that formally accounts for multi-state compliance risk as NimbusPay expands. Conduct periodic independent control assessments to verify that state compliance controls are operating effectively. Perform formal risk assessments that incorporate state regulatory requirements as threat scenarios so that new state-level obligations are identified. Require that any third parties or vendors handling NimbusPay customer data on its behalf also demonstrate compliance with the applicable state laws in the states where they operate. | NIST SP 800-53 Rev. 5 | Evan - Legal Compliance lead | In Progress | Quarterly

## Sheet1
Access Control | review access controls, implement configuration changes to make them more effective, code integrity validation | A.9.2.2 User access provisioning
Logging | Implement SIEM, enable AWS cloud trail and configure for suspicious activity, human check for reviewing logs | A.12.4.1 Event logging and A.12.4.3 Administrator and operator logs
Incident Response | incident response process, tabletop exercises, logging trails for AWS, SIEM configured to alert when suspicious activity takes places through admin accounts. Review incident response process, include proper root cause analysis, clear controls for mitigation, clear threat identification process and modeling, continuously refine, Establish roles and responsibilities | A.12.2.1 Controls against malware and A.16.1.1 Responsibilities and procedures and A.16.1.5 Response to information security incidents.
Software Development | Change management process before deploying changes, Critical changes should be reviewed, security. Security during all stages of development. | A.14.2.2 System changes control procedures and A.14.2.3 Technical review of applications after operating platform changes and A.14.2.8 System security testing
Supplier Relationships | Document formal vendor risk management program, Ensure all relelvant information security requirements are established and agreed upon, ensure that the customer being onboarded follows proper risk management, cybersecurity, and legal compliance requirements. | A.15.1.1 Information security policy for supplier relationships. A.15.1.2 Addressing security within supplier agreements
Information Security Training | Formal security awareness training for all employees. This could be through a monthly class or webinar. | A.7.2.2 Information security awareness, education and training.
Backups | Test backups and implement regular backups as needed and according to policy. | A.12.3.1 Information backup
Malware | User training against social engineering, encryption for data at rest and in motion through symmetric and asymmetric encryption. Antivirus, firewalls IDS systems, backups. | A.12.2.1 Controls against malware and A.18.1.4 Privacy and protection of personally identifiable information
Security within Supplier agreements | formal review and audit of third parties (if allowed) | A.15.1.2 Addressing security within supplier agreements
Threats | threat modeling, staying up to date with the recent cybersecurity threats and newest hacking methods. Implement SIEM, logging, and IDS. | A 5.7 Threat Intelligence
Handling of Assets | formal process for disciplinary action for those who commit a security breach. Update procedures for handling assets in accordance with information handling scheme. | A.7.2.3 Disciplinary process and A.8.2.3 Handling of assets
Access Reviews | Update access review process and implement it consistenly across departments. | A.9.2.1 User registration and de-registration and A.9.2.2 User access provisioning and A.9.2.3 Management of privileged access right
Public Network | Create clear policies (or update existing policies) how messaging and project management tools can be used safely. Make sure they will be used securely when connected to public networks and that no sensitive information is shared through messaging platforms. | A.13.2.3 Electronic messaging and A.14.1.2 Securing application services on public network
Encryption | Review encryption methods and make sure that data in motion and at rest is encrypted effectively using symmetric and assymetric encryption. | A.14.1.3 Protecting application services transactions
Disaster Recovery | Standardize reporting and documenting processes and procedures to ensure continuity for information security, review these reports periodically, put measures in place so the incident is not repeated using data. | A.16.1.6 Learning from information security incidents and A.17.1.2 Implementing information security continuity and A.17.1.3 Verify, review and evaluate information security continuitiy.